## Sheet1
Names | tasks | week1 | week2 | week3 | week4 | week5 | week6 | week7 | week8 | week9 | week10 | week11 | week12
Jeff whitford
networking module
client design
server design
navigation module
integration and testing
steve jones
circuit board design
CB revision 1
CB revision 2
navigation module
parts ordering
integration and testing
grant dare
vision research
camera design
vision module
integration
james moss
mechanical research
wheel design
mechanical design
motor control module
milestones
| sprint 1 |  |  | design, analysis, order parts
| sprint 2 |  |  |  |  | first prototype,individual design demo
| sprint 3 | [6 empty] | second prototype, individual design demo
| sprint 4 | [8 empty] | integration, individual final demo
| sprint 5 | [10 empty] | testing for final submission
| assessment dates |  |  |  |  | design demo due |  |  | prototype demo |  | individual final demo |  |  | FINAL