## Sheet1
Names | tasks | week1 | week2 | week3 | week4 | week5 | week6 | week7 | week8 | week9 | week10 | week11 | week12
Jeff whitford
| networking module |  | In progress
client design
server design
navigation module
integration and testing
steve jones
circuit board design
| CB revision 1 |  |  |  | first submission
CB revision 2
kicker dribbler and lobber
navigation module
parts ordering
integration and testing
grant dare
vision research
camera choice
vision module
integration
james moss
mechanical research
wheel design
mechanical design
motor control module
milestones
| sprint 1 |  |  | design, analysis, order parts
| sprint 2 |  |  |  |  | first prototype,individual design demo
| sprint 3 | [6 empty] | second prototype, individual design demo
| sprint 4 | [8 empty] | integration, individual final demo
| sprint 5 | [10 empty] | testing for final submission
| assessment dates |  |  |  |  | design demo due |  |  | prototype demo |  | individual final demo |  |  | FINAL