## Sheet1
Names | tasks | week1 | week2 | week3 | week4 | week5 | week6 | week7 | week8 | week9 | week10 | week11 | week12
Jeff whitford
| networking module |  | In progress
client design
server design
navigation module
Gui devlopement
integration and testing
steve jones
circuit board design
| CB revision 1 |  |  |  | first CB submission
CB revision 2
kicker dribbler and lobber
navigation module
parts ordering
integration and testing
grant dare
| vision research |  | in pogress
camera choice
vision module
integration
james moss
| mechanical research |  | In progress
| wheel design |  |  |  | submission
mechanical design
motor control module
milestones
| sprint 1 |  |  | design, analysis, order parts
| sprint 2 |  |  |  |  | first prototype,individual design demo
| sprint 3 | [6 empty] | second prototype, individual design demo
| sprint 4 | [8 empty] | integration, individual final demo
| sprint 5 | [10 empty] | testing for final submission
| assessment dates |  |  |  |  | design demo due |  |  | prototype demo |  | individual final demo |  |  | FINAL